## EXAMPLE - Weekly Gantt Plan
Vr2023.10.16 WEEKLY GANTT 3Yr Project
PROJECT NAME | Deceptive Storytelling using AI Planning and ChatGPT
STUDENT NAME | Minjun Choi
STARTING DATE | 25th Sept 2023
KEY DATES | WEEK7 15th March 2024(Code Submitted), | WEEK8 12th April 2024(Report and Screencast submitted)
[7 empty] | PHASE ONE | [14 empty] | PHASE ONE | [14 empty] | PHASE ONE | [14 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE TWO | [14 empty] | PHASE TWO | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | Dec. 18th |  |  |  |  | Dec. 25th |  |  |  |  | Jan 1st |  |  |  |  | Jan 8th |  |  |  |  | Jan 15th |  |  |  |  | Jan 22nd |  |  |  |  | Jan 29th |  |  |  |  | Feb 6th |  |  |  |  | Feb 13th | [19 empty] | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE |  | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Concept Brainstorming |  | 2023-09-25 | 2023-10-02 | 7 | 100%
1.2 | Searching for the use of Deceptive Storytelling using AI Planning |  | 2023-10-02 | 2023-10-09 | 7 | 100%
1.2.1 | Research for the pipeline of AI planning that generates story |  | 2023-10-08 | 2023-10-15 | 7 | 100%
1.2.2 | Run the pipeline and experiment with it |  | 2023-10-09 | 2023-10-16 | 7 | 40%
1.2.3 | Modify the pipline and change any feature of the generated story |  |  |  |  | 70%
1.2.4 | Try to generate deceptive story by modifying the pipeline |  |  |  |  | 60%
1.3 | Search for the method of evaluation of deceptiveness of a story |  |  |  |  | 50%
1.3.1 | Run the pipeline or test some data on this evaluation method
1.3.2 | Choose or modify the method that will be suitable for the project |  |  |  |  | 0%
1. | [5 empty] | 0%
1. | [5 empty] | 0%
1. | [5 empty] | 0%
2 | Project Experiments and Coding
2.1 | Modify the Pipeline and generating deceptive storys |  |  |  |  | 0%
2.1.1 | Generate enough data(decptive storys to be evaluated) |  |  |  |  | 0%
2.1.1 | Improve or Change the features of the Pipline |  |  |  |  | 0%
2.2 | Conduct the evaluation method on some sample data |  |  |  |  | 0%
2.2.1 | Analyse the statistics of evaluation |  |  |  |  | 0%
2.2.2 | Improve or Choose the method of evaluation based on the statistics |  |  |  |  | 0%
2.3. | Write some draft versions of Introduction
2.3.1 | Write about the motivation and ideas of the project |  |  |  |  | 0%
2.3.2 | Citations of ideas and motivations about the project |  |  |  |  | 0%
2.3.3 | Summerise and visualize the experiments |  |  |  |  | 0%
2.4 | Run experiments on the code |  |  |  |  | 0%
2.4.1 | Write codes for the experiments on deceptive story generator |  |  |  |  | 0%
2.4.2 | Write codes or records of evaluation of deceptiveness of storys |  |  |  |  | 0%
2.4.3 | Write codes of the full pipeline and its evaluation |  |  |  |  | 0%
0%
0%
0%
3 | Experiment Finalization, Polishing the Code for the pipeline, Report writing |  |  |  |  | 0%
3.1 | Analysis the statistics of the most optimal method of evaluation |  |  |  |  | 0%
3.1.1 | Search for evidence that current method is most suitable for the project |  |  |  |  | 0%
3.1.2 | Search for the improvements of the method and enhanced versions of it |  |  |  |  | 0%
3.2 | Analysis the performance of the pipline that uses AI Planning |  |  |  |  | 0%
3.2.1 | Search for the improvements on the final version of pipline |  |  |  |  | 0%
3.2.2 | Other ideas and cases of other AI planning |  |  |  |  | 0%
3.3 | Finish the Code of the pipeline and experiments, evaluations |  |  |  |  | 0%
3.3.1 | Clean codes and comments |  |  |  |  | 0%
3.3.2 | Check for any error and submit the code |  |  |  |  | 0%
0%
3.4 | Write the Report in the correct format |  |  |  |  | 0%
3.4.1 | Look for the references that can backup my idea |  |  |  |  | 0%
3.4.2 | Finalize the structure of the report and plan the conclusion of the project |  |  |  |  | 0%
0%
0%
0%
4. | Screen Casting and Report completing, QnA preperation |  |  |  |  | 0%
4.1 | Report Finishing |  |  |  |  | 0%
4.1.1 | Get some feedback and finalize the report |  |  |  |  | 0%
4.2 | Screen Cast |  |  |  |  | 0%
4.2.1 | Prepare some images and animations |  |  |  |  | 0%
4.2.2 | Record some audio and video |  |  |  |  | 0%
4.2.3 | Edit the Screen Casting video |  |  |  |  | 0%
4.3 | QnA Preperation |  |  |  |  | 0%
4.3.1 | Revise how this project has been conducted |  |  |  |  | 0%
0%
0%

## BLANK - Weekly Gantt Planning
WEEKLY GANTT PROJECT PLANNING TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1
1.1 | [5 empty] | 1%
1.1.1 | [5 empty] | 2%
1.2 | [5 empty] | 3%
1.3 | [5 empty] | 0%
1.4 | [5 empty] | 0%
1.5 | [5 empty] | 0%
1.6 | [5 empty] | 0%
2
2.1 | [5 empty] | 0%
2.2 | [5 empty] | 0%
2.3 | [5 empty] | 0%
2.4 | [5 empty] | 0%
3
3.1 | [5 empty] | 0%
3.2 | [5 empty] | 0%
3.2.1 | [5 empty] | 0%
3.2.2 | [5 empty] | 0%
3.3 | [5 empty] | 0%
3.3.1 | [5 empty] | 0%
4
4.1 | [5 empty] | 0%
4.2 | [5 empty] | 0%
4.3 | [5 empty] | 0%
4.4 | [5 empty] | 0%

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.